## EVM Calculations
Metric | Value | Description
Planned Value (PV) | 40 | Total planned story points for Sprint
Earned Value (EV) | 40 | Completed story points
Actual Cost (AC) | 38 | Actual effort/cost spent
Schedule Variance (SV) | EV - PV = 0 | On schedule
Cost Variance (CV) | EV - AC = +2 | Under budget
Schedule Performance Index (SPI) | EV / PV = 1.0 | Schedule efficiency
Cost Performance Index (CPI) | EV / AC ≈ 1.05 | Cost efficiency